**Computing Final Year Project – Design : 2017/2018**

**Submissions and Dates**

The Final Year Project enables students to take responsibility for a complete development project throughout the design and planning aspects of the project. This allows for the integration of knowledge and experience. An incremental approach will employed in producing an implementation to meet agreed acceptance criteria.

There will be a number of submissions/milestones throughout the semester. At each of these, the student is required to submit a piece of work. The supervisors will decide if progress to date is acceptable.

**In relation to module co-ordination:**

Helen Fitzgerald, [helen.fitzgerald@ittralee.ie](mailto:helen.fitzgerald@ittralee.ie), is the Project Co-ordinator.

The role of the Project Co-ordinator is to :

* + Assign supervisors to projects.
  + Establish submission dates and convey these details to students and their supervisors.
  + Collate final submissions.

**Submission 1: Project Vision Statement** Thursday 14th September 2017

One paragraph on the vision ofyour project.

This is used to assign supervisors.

**Submission 2: Project Proposal Document** Week of Monday 9 October 2017

Project Title and Objectives

Research areas defined and research commenced

Initial key citations and references identified

Initial research question Identified.

Defend your research question to the pool on **Thursday 12th October.**

**Submission 3 Project Plan** Week ofMonday 23rd October 2017

Main research chapter in Literature Review completed

Table Of Contents of remaining Literature Review.

Risk analysis including platform issues.( Table format)

Vision Document **(Determined in association with SQA Module)**

**Milestone: Project Specification** Monday 13th November 2017

Functional Specification: **(Determined in association with SQA Module)**

**Milestone: Formal Design** Monday 29thth November 2017

Detailed systems design document **(Determined in association with SQA Module)**

Sprints ( First draft)

Key Class Diagrams

**Submission 3: Prototype & Design Presentation** Wednesday 13th December 2017

Literature Review Completed

Design Documents

User Stories/Test plan

Some Increments (agreed with supervisor) implemented/tested

Electronic submissions onto the X drive.

**FYP Design Presentations 13**th  **December 2017.**